## Change Form
Project Name: |  | StimuPop: Excel to PowerPoint Converter |  |  |  | This form will document all changes/additions from start to finish. Each new item will be added to the list so the complete history can be viewed at a glance, including clarifications from the vendor
Job Number: |  | 201-01 AI DEVELOPMENT
Date | Version vs Guide | Section | Type of Request | Description of Request | Change / Error | John's Response | Change Check | Project Team Comments (if Incomplete)
2026-01-29 | User Guide | 2. Getting Started | Instruction Update | In step 3, update this instruction: “Double-click 'StimuPop.exe' to launch the application” | Change | Done | Complete
2026-01-29 | User Guide | 2. Getting Started | Instruction Update | It would be helpful to add clarifying instructions that you need to ctlr and click on the local link http://localhost:8501 to get it to open in the browser window. | Change | Done | Complete
2026-01-29 | Stimupop v6.1 | 2. Getting Started | Launching | Whenever I first try to open the link in my browser, I get an error message warning me that the website is uncategorized. However, if I hit continue, exit the window, and then Ctrl-click again on the link, it opens perfectly fine. Is that something that can be fixed? | Error | Done | Incomplete | This error still occurs occasionally, but sometimes it doesn't…
2026-01-29 | User Guide | 4. Using StimuPop | Instruction Update | In step 1, update this instruction: “Double-click 'StimuPop.exe' to launch the application” | Change | Done | Complete
2026-01-29 | User Guide | 4. Using StimuPop | File Uploading | When I first tried to upload the test files I created, I got a "TypeError: Failed to fetch dynamically imported modue" error message on both files. But then I closed out of the application altogether and went back in, and the same files uploaded perfectly fine. | Error | Done | Complete
2026-01-29 | User Guide | 5. Configuration Options | Instruction Update | In the User Guide, I would clarify that the “Per-Column Formatting” options under the advanced settings are only available when using Blank Mode. | Change | Done | Complete
2026-01-29 | User Guide | 5. Configuration Options | Instruction Update | Is the “Layout Position (Blank mode)” only applicable to the Blank Mode, or is it also usable with the Template Placeholders mode? On screen, it has (Blank mode), but this section also appears when I’m on Template Placeholder mode. Perhaps remove the (Blank mode) from on-screen. | Change | Done | Complete
2026-01-29 | Stimupop v6.1 | Generate Presentation | Running Presentation | The first time I clicked generate presentation, this error popped up "TypeError: Failed to fetch dynamically imported modue", but when I opened it in the newer version, it ran without any issues. | Error | Done | Complete
2026-01-30 | Stimupop v6.1 | Image Sizing | Max Width/Max Height | Change the minimum to zero so we have the full range of sizes. For example, for our thumbnail images, we need sizes 1.25W x1.25H on a 3.5W x 1.25H slide size. | Change | Done | Complete | Since we also create thumbnails, it would be nice to use program for all size Powerpoint slides. See attached example.
2026-01-30 | Stimupop v6.1 | Generate Presentation | Add new feature | Can we add an option for pictures only? (No text needed from excel file for pop-up images). Right now, we are getting this to work for this example by adding a text box and then find/replace the word. | Change | Done | Complete | Since we also create pop-up images, it would be nice to use program for this as well. See attached example.
2026-01-30 | Stimupop v6.1 | Layout Position | Text Top Position (inches) | Change the minimum to zero so we have the full range of sizes. | Change | Done | Complete
2026-01-30 | Stimupop v6.1 | Image Sizing | Update text | Remove (Blank mode only) since I am able to use this feature for template placeholders (NEW) | Change | Done | Complete
2026-01-30 | Stimupop v6.1 | Layout Position | Update text | Add (Blank mode only) to Layout Position in the program | Change | Done | Complete
2026-01-30 | Stimupop v6.1 | Image Alignment | Update text | Add (Blank mode only) to Image Alignment in the program | Change | Done | Complete
2026-01-30 | User Guide | Template Mode | Add to user guide | Suggestion: Since you added this to the program, maybe you can just add a summary of it in the beginning of the Advanced Settings section | Change | Done | Complete
2026-01-30 | User Guide | Image Alignment | Move in user guide | Suggestion: Since image aligment follows Layout position, maybe you can move that explanation after layout position so it matches the program | Change | Done | Complete
2026-01-30 | User Guide | Text Spacing | Add to user guide | Suggestion: Add the note about text spacing here to match the program | Change | Done | Complete
2026-01-30 | Stimupop v6.1 | How To Use | Update text | Name the text placeholder (e.g., "TextBox 55") to Name the text placeholder (e.g., "TextBox 55") | Change | Done | Complete
2026-01-30 | User Guide | 3. Preparing Your Excel File | Instruction Update | For the example project I used, we don’t include a description on the variety card itself, so I didn’t need Column F. It would be helpful to elaborate in the instructions that you can add/remove/edit the columns as needed, as long as it matches the columns specified in the PPT template you upload. | Change | Done | Complete
2026-01-30 | Stimupop v6.1 | Configuration | Font Size (pt) | The Font Size should be consistent to match "Column Formatting" which allows for 8 - 48. Change the font size here to match instead of 10 - 32 | Change | Done | Complete
2026-01-30 | Stimupop v6.1 | PPT Export | Text Box Size Formmating | When the text of the item in columns D/E is too long, the text appears to wrap off the bottom of the PPT slide, I believe because the default text box is set to "Resize shape to fit text" (Under Format Shape > Shape Options > Text Box). Instead of setting that as the default, is there a way we could add an option to the program to select the text box to either "Resize shape to fit text" OR "Shrink text on overflow"? The Shrink option keeps everything in the specified text box space and doesn't let it wrap off the page. See Overflow Tab for examples | Change | Done | Complete
2026-01-30 | Stimupop v6.1 | Template Mode (NEW) | Presentation Display | When I try to run the same variety card list in 4 columns vs 5 columns, it gives me different results. The 4-column run seems to work perfectly fine, but the 5-column run doesn’t read the last row (Column F) and adds spacing in the wrong spot. I'm using the Template Placeholders (NEW) mode in both scenarios. The only thing I changed between the two was the C,D,E vs C,D,E,F Text Columns. I left everything else on default. I also modified the original template size-wise. See "4 Col vs 5 Col" Tab for examples. | Change | Done | Complete | Confirming I got this to work correctly, I believe the issue was the Placeholder Names (shapes in the PPT) were called different things in both templates and I didn't update them in the "Image/Text Placeholder Name" boxes
2026-02-02 | Stimupop v7.0 | Data Preview | Error Message | A couple of times, I got his error message when I tried to upload an Excel file: But then, when I close out of the app altogether and reopen it works fine | Error
2026-02-02 | Stimupop v7.0 | Text Spacing | Text Overflow Options | Thank you for adding that new option for Text Overflow!! However, when I select the "Shrink text on overflow" option it doesn’t seem to actually change that in the PPT presentation export. The text still wraps off the bottom and the TextBox itself it still defaulted to "Resize shape to fit text". Could you double-check that new function is actually working properly? | Change
2026-02-02 | Stimupop v7.0 | Configuration | Options for multiple elements | For some projects, we show variety cards slightly differently, either with multiple pictures and/or multiple text boxes. For example, showing the brand/product name at the top of the slide, an image in the middle, and price/size details at the bottom. Is there a way we could add/edit/remove the # of text boxes and/or images shown on each slide? I think we definitely can keep the default to 1 image + 1 text box, but perhaps add an option to add additional images/boxes as needed underneath the Image/Text Placeholder Name boxes - if possible. See "Multiple Elements" tab for examples | Change

## Multiple Elements
TextBox 1
Rectangle 1
TextBox 2
Rectangle 1
TextBox 1
TextBox 2
Rectangle 2

## Overflow Examples (hidden)
Is there any way to make the text at the bottom not wrap off the screen when the text is longer, like on these slides below? Or is that something we will need to manually adjust?

## 4 Col vs 5 Col (hidden)
4 Column Set up: |  |  |  |  | 5 Column Set up:
4 Column Excel File: |  |  |  |  | 5 Column Excel File:
A | B | C | D | E | A | B | C | D | E | F
SKU # | Image | Brand | Full Product Name | SKU Size/Price | SKU # | Image | Brand | Full Product Name | Flavor | SKU Size/Price
11 | #VALUE! | Cabot | Whole Milk Greek Yogurt Plain | 32oz Tub for $5.09 | 11 | #VALUE! | Cabot | Whole Milk Greek Yogurt | Plain | 32oz Tub for $5.09
4 Column PPT Template: |  |  |  |  | 5 Column PPT Template:
Slide size: 4.2W v 4.3H |  |  |  |  | Slide size: 4.2W v 4.3H

## Hidden Sheet (hidden)
Dropdown Colum G
Change | Complete
Error | Incomplete